## Project Timeline
PROCESS TIMELINE: High-level Milestones
PROCESS DETAILS AND NOTES
DATE | MILESTONE | POSITION | BASELINE | Position Adjusted | Date adjusted | Milestone adjusted | NOTES
2023-01-15 | Begin drafting Concept Paper | 25 | 0 | 25 | 2023-01-15 | Begin drafting Concept Paper | Concept Paper can be found on the Provost's Office website
2023-04-15 | Create plans for relevant consultations (external to UBC) + other needed data | 5 | 0 | 5 | 2023-04-15 | Create plans for relevant consultations (external to UBC) + other needed data | Data needed to successfully complete the Concept Paper for Provost approval
2023-05-15 | Deploy consultation plan | -10 | 0 | -10 | 2023-05-15 | Deploy consultation plan | If needed, request support from Provost Office and/or OPAIR
2023-08-15 | Finalize Concept Paper based on consults | -15 | 0 | -15 | 2023-08-15 | Finalize Concept Paper based on consults | If graduate program: submit completed Concept Paper to CoGS before submitting to Provost's O.
2023-09-01 | Develop budget and gain Dean and Provost Approvals | 10 | 0 | 30 | 2023-09-01 | Begin Senate-related process | Budget must be completed with the guidance of the Faculty's Finance Manager and based on identified needs/costs for the program
2023-09-01 | Begin Senate-related process | 30 | 0 | 10 | 2023-09-01 | Develop budget and gain Dean and Provost Approvals | Department/School/Faculty approvals vary. Provost approves Concept Paper and Budget
2023-10-01 | Submit Senate-required package to Senate Office | -25 | 0 | -25 | 2023-10-01 | Submit Senate-required package to Senate Office | Follow Senate Curriculum Guidelines. The Concept Paper transforms into the Senate-required Executive Summary.
2023-12-15 | Gain Senate Committees approvals (admissions and curriculum) | 7 | 0 | 7 | 2023-12-15 | Gain Senate Committees approvals (admissions and curriculum) | Senate Office advises on deadlines and needs
2024-01-01 | Begin tuition and fees process | -15 | 0 | -15 | 2024-01-01 | Begin tuition and fees process | Follow process and templates in Provost Office website
2024-02-15 | Gain Senate approval | 20 | 0 | 20 | 2024-02-15 | Gain Senate approval
2024-03-15 | Submit package for Board of Governors approval | -25 | 0 | -25 | 2024-03-15 | Submit package for Board of Governors approval | After Senate approval. Curriculum is submitted by the Senate Office and Tuition schedule is submitted by Provost's Office
2024-06-15 | Submit package for Ministry approval | 10 | 0 | 10 | 2024-06-15 | Submit package for Ministry approval | Provost's Office works with program proponents to ensure all requirements are met for submission

## Project Data Sorted (hidden)
Sort the dates to populate the timeline in chronological order
|  |  | data analysis | [5 empty] | Actual data to chart, which is fed into the Project Timeline worksheet via hidden columns F-H.
| start row | 5 | TIE BREAK | RANK | DATE | MILESTONE | POSITION | NUM | RANK Sorted | DATE | MILESTONE | POSITION
| last entry | 16 | 12 | 1 | 2023-01-15 | Begin drafting Concept Paper | 25 | 11 | 12 | 2023-01-15 | Begin drafting Concept Paper | 25
|  |  | 11 | 2 | 2023-04-15 | Create plans for relevant consultations (external to UBC) + other needed data | 5 | 10 | 11 | 2023-04-15 | Create plans for relevant consultations (external to UBC) + other needed data | 5
|  |  | 10 | 3 | 2023-05-15 | Deploy consultation plan | -10 | 9 | 10 | 2023-05-15 | Deploy consultation plan | -10
|  |  | 9 | 4 | 2023-08-15 | Finalize Concept Paper based on consults | -15 | 8 | 9 | 2023-08-15 | Finalize Concept Paper based on consults | -15
|  |  | 7 | 5 | 2023-09-01 | Develop budget and gain Dean and Provost Approvals | 10 | 7 | 8 | 2023-09-01 | Begin Senate-related process | 30
|  |  | 8 | 5 | 2023-09-01 | Begin Senate-related process | 30 | 6 | 7 | 2023-09-01 | Develop budget and gain Dean and Provost Approvals | 10
|  |  | 6 | 7 | 2023-10-01 | Submit Senate-required package to Senate Office | -25 | 5 | 6 | 2023-10-01 | Submit Senate-required package to Senate Office | -25
|  |  | 5 | 8 | 2023-12-15 | Gain Senate Committees approvals (admissions and curriculum) | 7 | 4 | 5 | 2023-12-15 | Gain Senate Committees approvals (admissions and curriculum) | 7
|  |  | 4 | 9 | 2024-01-01 | Begin tuition and fees process | -15 | 3 | 4 | 2024-01-01 | Begin tuition and fees process | -15
|  |  | 3 | 10 | 2024-02-15 | Gain Senate approval | 20 | 2 | 3 | 2024-02-15 | Gain Senate approval | 20
|  |  | 2 | 11 | 2024-03-15 | Submit package for Board of Governors approval | -25 | 1 | 2 | 2024-03-15 | Submit package for Board of Governors approval | -25
|  |  | 1 | 12 | 2024-06-15 | Submit package for Ministry approval | 10 | 0 | 1 | 2024-06-15 | Submit package for Ministry approval | 10